## Implementation Roadmap
Week | Milestone | Description | Owner | Status
0 | Enterprise Setup | Enable enterprise accounts (Cursor, GitHub, Azure DevOps) and publish SOPs | Security Architect | Planned
1 | Codespaces Configuration | Configure policies, devcontainer images, restrict extensions | Automation Engineer | Planned
2 | Pipeline Modernization | Reconfigure Azure DevOps pipelines to OIDC + Key Vault integration | Offshore Security Engineer | Planned
3-4 | Pre-Production Pilot | Run pilot deployment in pre-production; collect metrics | Application SME | Planned
5 | Security Validation | Perform compliance checks and map to CIS/CSA/NIST standards | Principal Security Architect | Planned
6 | Production Go-Live | Cutover to production with governance sign-off | Senior Project Director | Planned